## Start here
GxP Quality Hub — release decision workbook
Prepared 2026-10-25 for Dinesh Naik (Engagement lead). Synthetic data. The decision path stays No-AI (OD-08). Since 26 Oct an optional, off-by-default advisory Q&A exists (Stage 44, OD-40); it does not change the 40 approvals, but enabling it needs its own approval reference for ai.enabled.
Who fills the yellow cells | Only you. The hub's release check refuses approvals that name an agent, assistant, orchestrator, bot, system or AI. Claude prepared everything else and signed nothing.
Step 1 | Type your full name once in C13 (Approver) and the date in C14 (ISO, e.g. 2026-10-26).
Step 2 | Sheet 'Sign-offs (40)': read the evidence named in column F, then choose APPROVED, REJECTED or OPEN in column G. Leave OPEN when unsure. A row needs no other typing: references are generated for you (you may override columns I and J).
Step 3 | Sheet 'Security (T-10)': pick one option per item and put a short reason. Sheet 'Monitoring (T-09)': choose option A or B.
Step 4 | Save the file, then run: py -3.14 release_check.py validate --workbook <this file> (it only reads and reports).
Step 5 | When validate is clean, run: py -3.14 release_check.py evaluate --workbook <this file> It builds the approvals file, records the deviation decisions in a sandbox copy, runs the golden comparison and prints the repo's own GO / NO-GO. Your repository is not modified.
What 'GO' means here | GO (shadow): the hub runs beside the legacy system on synthetic data. It does not mean production cutover; the five CUT-n approvals stay OPEN.
Approver (full name)
Approval date (ISO)
Live counts

## Technical (20)
Technical criteria (evidence only; a pass is not an approval). Source: docs/30-release/evidence/gate-results.json
ID | Result in repo today | Criterion / note | Evidence file | What clears it | Who | Status after this session
G1 | fail | golden diff: unapproved differences = 0 — golden-compare exit 6: every entry UNAPPROVED because DV-01..DV-11 are proposed (OD-S12-13 open); cannot pass before Dinesh decides | docs/30-release/evidence/s30-log-06-golden-compare.txt | Record a preserve-or-fix decision for DV-01..DV-11 (sheet Sign-offs, rows AP-DV-*). The tool then marks each as an approved deviation and the golden comparison must exit 0. | You (decisions) + Claude (run) | OPEN: needs your 11 deviation decisions, then the comparison re-run.
G2 | pass | replay-safety suite (AC-INT-04/05) passes — group I6 43/43 (TST_INT, replay safety) | docs/30-release/evidence/s30-regression-groups.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G3 | pass | verify-audit ok — verify-audit ok on the sandbox store; also ok after refusal, authority flip, L3, restore (logs 10, 16, 19, 22, 25) | docs/30-release/evidence/s30-log-04-verify-audit.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G4 | pass | verify-projection 0 mismatches — group I45 91/91 (projection tests); no stand-alone verify-projection on a production store (none exists) | docs/30-release/evidence/s30-regression-groups.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G5 | pass | No-AI tripwire: deny-list clean, no egress, model_calls_total = 0 (shipped default ai.enabled=false; Stage 44 adds a gated, off-by-default Azure OpenAI path) — tripwires zero in the groups run; hub.admin release-checklist evaluates G5 (log 09b) | docs/30-release/evidence/s30-regression-groups.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G6 | pass | secret scan 0; deletion-path grep 0 — scan evaluated by hub.admin release-checklist | docs/30-release/evidence/s30-log-09b-release-checklist-no-mark.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G7 | pass | backup/restore rehearsal checksum match — backup/restore rehearsal evaluated by hub.admin; also logs 07, 08, 21, 22 | docs/30-release/evidence/s30-log-09b-release-checklist-no-mark.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G8 | pass | Zone H negative tests (AC-GATE-09/11/12) pass — group I8a 35/35 (TST_GATE, TST_REV) | docs/30-release/evidence/s30-regression-groups.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G9 | pass | planted-string fixture suite (86/22/44) 0 effects — group I6 (planted-string and untrusted-source tests) | docs/30-release/evidence/s30-regression-groups.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
G10 | pass | determinism: bit-identical across PYTHONHASHSEED/TZ/locale — TST_CO_13 inside group B (41 of 42 executed ok-or-skipped; the 1 failure is TST_CO_05_c, S30-DEV-03) | docs/30-release/evidence/s30-regression-groups.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-01 | pass | backup manifest of the legacy baseline verifies (rc 0) before and after every rehearsal — manifest rc 0 before and after the rehearsal; rc 0 before and after every group | docs/30-release/evidence/s30-rehearsal-summary.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-02 | pass | L1 code revert rehearsed on a sandbox clone — revert of the Stage 31 squash commit in a clone gives exactly the pre-Stage-31 hub/ and tests/hub (log 28); revert-of-revert restores main (log 31) | docs/30-release/evidence/s30-log-31-l1-tree-restored.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-03 | pass | L2 hub-state backup / restore rehearsed on a sandbox copy — backup, restore, corrupt-backup refusal exit 21 (log 24) | docs/30-release/evidence/s30-log-22-verify-audit-after-restore.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-04 | pass | L3 authority flip and flip back rehearsed on a sandbox copy, audit chain verifies — flip refused without reference (exit 2); held with a sandbox marker; flip-to-shadow; two CONFIG_CHANGED records; chain ok | docs/30-release/evidence/s30-audit-config-changed.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-05 | not_run | full hub regression: every group green and executed = expected — 11 of 31 groups run here; the full regression at the final HEAD is the orchestrator's (OD-23) | docs/30-release/evidence/s30-regression-groups.txt | Full 31-group regression on the final HEAD: every group green and executed = expected. | Claude (run) | DONE: green on Python 3.14.6, clean main a2b4828, 31 of 31 groups, 586 of 586 executed = expected at main a2b4828, before Stage 44 (main e62c9b4: 33 groups, 613 executed, 1 skip, Python 3.13 cloud sandbox; Python 3.14 re-run pending) (1 skip: python3.9 not installed). Not yet recorded in the repo's gate-results.json.
T-06 | pass | characterization harness: no failure except the registered CT-13 Node drift — only CT-13 fails (Node patch drift, S24-DEV-04, registered) | docs/30-release/evidence/s30-characterization.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-07 | pass | shipped configuration posture: shadow, empty Zone H holders, loopback, schedule off, synthetic data — hub.release posture clean on shipped defaults; hub-hardening workflow not installed (only the legacy verify.yml exists); no config sets an authority switch | docs/30-release/evidence/s30-log-23-posture-after-restore.txt | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-08 | pass | F-29-01 fixed with a test (verify-audit exits 17 on a malformed anchor line) — F01..F03 green; exit 17 and no traceback | tests/hub/test_tst_hub_stg30_f2901.py | Nothing: already passes in the repo's evidence. | - | No change needed (still pass; re-checked by the final evaluate step).
T-09 | fail | monitoring coverage for the release window: persisted metrics, alert delivery and an owner — no persisted metrics, no alert delivery, no on-call (F-29-03, D-31-01, D-31-08) | docs/31-observability/alert-catalog.md | Choose option A (accept manual monitoring for the release window) or B (wire persisted metrics) on sheet 'Monitoring (T-09)'. | You (choice) | OPEN: needs your choice. Draft: docs in 06_Release_Readiness/T-09_Monitoring_Acceptance_Draft.md
T-10 | fail | every High vulnerability and every open High finding has a recorded decision by the Engagement lead — VR-02, VR-03, VR-04 High items have no accepted disposition; F-11 and risk registers open | docs/27-hardening/vulnerability-disposition.md | Record a decision for VR-02, VR-03, VR-04 and F-11 on sheet 'Security (T-10)'. | You (decisions) | OPEN: needs your 4 decisions. Draft: 06_Release_Readiness/T-10_Security_Decisions_Draft.md

## Sign-offs (40)
Approval register: 40 records. Yellow = yours. Recommended defaults are proposals from the repo (OD-32), not decisions.
Level: GO-shadow = needed for 'GO (shadow)'. CUT-n = needed only for that cutover step; leave OPEN unless you are ready to cut over.
ID | Scope | Needed for | Decision to take | Agent recommended default (not a decision) | Read first | YOUR DECISION | Your note (optional) | approval_ref (auto if empty) | evidence_ref (auto if empty) | Check
AP-REL-01 | REL | GO (shadow) | Release decision (go / no-go) for the hub in shadow mode | no-go until every technical criterion passes and AP-GATE-*, AP-OPS-* (REL) are recorded | docs/30-release/go-no-go-criteria.md; this workbook, sheet Technical | OPEN
AP-GATE-G1 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G1: golden diff: unapproved differences = 0 | acknowledge only after reading the evidence file named in gate-results.json; G1 cannot pass while any DV row is proposed | docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-GATE-G2 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G2: replay-safety suite (AC-INT-04/05) passes | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-regression-groups.txt | OPEN
AP-GATE-G3 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G3: verify-audit ok | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-log-04-verify-audit.txt | OPEN
AP-GATE-G4 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G4: verify-projection 0 mismatches | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-regression-groups.txt | OPEN
AP-GATE-G5 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G5: No-AI tripwire: deny-list clean, no egress, model_calls_total = 0 (shipped default ai.enabled=false; Stage 44 adds a gated, off-by-default Azure OpenAI path) | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-regression-groups.txt | OPEN
AP-GATE-G6 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G6: secret scan 0; deletion-path grep 0 | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-log-09b-release-checklist-no-mark.txt | OPEN
AP-GATE-G7 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G7: backup/restore rehearsal checksum match | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-log-09b-release-checklist-no-mark.txt | OPEN
AP-GATE-G8 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G8: Zone H negative tests (AC-GATE-09/11/12) pass | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-regression-groups.txt | OPEN
AP-GATE-G9 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G9: planted-string fixture suite (86/22/44) 0 effects | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-regression-groups.txt | OPEN
AP-GATE-G10 | REL | GO (shadow) | Human acknowledgement of the evidence for gate G10: determinism: bit-identical across PYTHONHASHSEED/TZ/locale | acknowledge after reading the evidence file named in gate-results.json | docs/30-release/evidence/s30-regression-groups.txt | OPEN
AP-DV-01 | CUT | G1 + CUT-4 | Preserve-or-fix decision for DV-01: SQL month-end total 742,956.61 (join fan-out) becomes 622,826.44 | fix (adopt the hub figure) for CUT-4; keep legacy report running as comparator | hub/coexistence/seed_s20.json (DV-01); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-02 | CUT | G1 + CUT-3 | Preserve-or-fix decision for DV-02: replayed message: legacy DUPLICATE 64 becomes NOOP_DUPLICATE 67 / REVISED_CONFLICT | fix | hub/coexistence/seed_s20.json (DV-02); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-03 | CUT | G1 + CUT-3 | Preserve-or-fix decision for DV-03: quantity out of range: legacy REJECTED 154 becomes NEGATIVE_VALUE flag, item kept | change of class: adopt as built | hub/coexistence/seed_s20.json (DV-03); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-04 | CUT | G1 + CUT-4 | Preserve-or-fix decision for DV-04: Java blank amounts: silently skipped becomes UNPARSABLE_AMOUNT quarantine | fix | hub/coexistence/seed_s20.json (DV-04); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-05 | CUT | G1 + CUT-2 | Preserve-or-fix decision for DV-05: JS tolerance with 'abc' / null becomes E-POL-INPUT-INVALID | fix | hub/coexistence/seed_s20.json (DV-05); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-06 | CUT | G1 + CUT-2 | Preserve-or-fix decision for DV-06: unknown region / year 999999 becomes the same value marked defaulted | accept the additive marker | hub/coexistence/seed_s20.json (DV-06); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-07 | CUT | G1 + CUT-3 | Preserve-or-fix decision for DV-07: reconcile overwrites status in place becomes append-only outcomes (DV-07a: outcome classification EXCEPTION 8,109 etc.) | fix, after Dinesh has seen the 7,903 UNMATCHED_REF volume | hub/coexistence/seed_s20.json (DV-07); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-08 | CUT | G1 + CUT-4 | Preserve-or-fix decision for DV-08: night-shift distinct objects 118 vs 500 (reference query, no batch job built; weak evidence) | do not cut over this figure; keep legacy authoritative until a hub job exists | hub/coexistence/seed_s20.json (DV-08); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-09 | CUT | G1 + CUT-3 | Preserve-or-fix decision for DV-09: invalid gateway event: counted, not stored becomes quarantined, stored (label MISSING_ENVELOPE_FIELD) | fix, with the corrected label | hub/coexistence/seed_s20.json (DV-09); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-10 | CUT | G1 + CUT-3 | Preserve-or-fix decision for DV-10: partner outcomes: exact ref_id matching, most legacy-ACCEPTED rows become EXCEPTION / UNMATCHED_REF (proposed row) | fix (exact match, BEH-INT-08) | hub/coexistence/seed_s20.json (DV-10); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-DV-11 | CUT | G1 + CUT-2 | Preserve-or-fix decision for DV-11: JS partial-year threshold: prefix match 15000 becomes 999999 defaulted (proposed row, DEV-29) | fix (4-digit year required) | hub/coexistence/seed_s20.json (DV-11); docs/30-release/evidence/s30-log-06-golden-compare.txt | OPEN
AP-CUT-1 | CUT | CUT-1 | Decision to make 'decision and evidence record, audit' authoritative (CUT-1) | decide last of the value-bearing steps only after the Zone H and closure questions are answered; keep shadow until then | docs/14-transformation/cutover-plan.md; docs/30-release/release-approvals.md | OPEN
AP-CUT-2 | CUT | CUT-2 | Decision to make 'rule evaluation' authoritative (CUT-2) | first step in the recommended order (CUT-2, CUT-1, CUT-3, CUT-4, CUT-5); needs DV-05, DV-06, DV-11 and OD-S12-04 | docs/14-transformation/cutover-plan.md; docs/30-release/release-approvals.md | OPEN
AP-CUT-3 | CUT | CUT-3 | Decision to make 'intake and reconcile outcomes' authoritative (CUT-3) | after CUT-1 and CUT-2; needs a named consumer and a decision to stop the in-place legacy reconcile | docs/14-transformation/cutover-plan.md; docs/30-release/release-approvals.md | OPEN
AP-CUT-4 | CUT | CUT-4 | Decision to make 'metrics, month-end and night-shift figures' authoritative (CUT-4) | after CUT-3; needs consumers named and the OD-S12-01/-02/-08 definitions | docs/14-transformation/cutover-plan.md; docs/30-release/release-approvals.md | OPEN
AP-CUT-5 | CUT | CUT-5 | Decision to make 'automation and exposure' authoritative (CUT-5) | last; keep loopback-only and the scheduler off unless Dinesh decides otherwise (D-27-09, HAR-10) | docs/14-transformation/cutover-plan.md; docs/30-release/release-approvals.md | OPEN
AP-OPS-01 | REL | GO (shadow) | target host and promotion path named and approved (environment-promotion-plan.md) | there is no production host; name one or accept shadow-on-the-laptop as the only environment | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-02 | REL | GO (shadow) | rollback authority, rollback triggers and who may call them | Dinesh is the only rung (F-29-07); record that explicitly | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-03 | REL | GO (shadow) | cutover window, change freeze and communications | no window exists; choose one only when a real consumer exists | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-04 | REL | GO (shadow) | off-device copy of the baseline and the hub backups (HAR-09, F-29-02) | approve an encrypted off-device copy (HAR-09) or accept the single-device risk in writing | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-05 | REL | GO (shadow) | monitoring owner and alert channel for the release window (D-31-08, F-29-03) | manual evaluation (RB-00) until a second human exists (D-31-08) | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-06 | REL | GO (shadow) | manual walkthroughs TST-REV-03 / 04 / 08 signed or explicitly left open (D-27-08) | leave open and say so, or perform and sign the three walkthroughs | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-07 | REL | GO (shadow) | runtime floor and Python 3.12+ evidence (D-27-02) | keep the 3.10 floor as shipped; run 3.12 / 3.13 evidence in the orchestrator cloud before any exposure | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-08 | REL | GO (shadow) | install the hardening CI file under .github with pinned SHAs, or not (D-27-03, HAR-07) | do not install CI now; decide with the SHA pins when a remote exists | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-09 | REL | GO (shadow) | legacy Dockerfile / compose hardening, or leave the legacy files as they are (D-27-06) | leave the legacy files unchanged (frozen path); the hardened recipe is in deployment-strategy.md as a proposal | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-10 | REL | GO (shadow) | wire the Stage 28 / 31 mechanisms before release, or release without them (D-28-01, D-28-02, D-31-01, D-31-02) | release without wiring (as built); wiring is a separate approved change | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-11 | REL | GO (shadow) | residual risks RS / RP / VA / RTR / F-xx accepted, rejected or carried (none is accepted by any stage) | carry every risk as open; accept none by default | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-12 | CUT | CUT-2/CUT-3/CUT-4 | consumers of the legacy outputs identified and a re-pointing owner named (U-14-01) | name the consumers or keep CUT-2..CUT-4 closed | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN
AP-OPS-13 | CUT | CUT-1 | real Zone H holders named, only if the Zone H gate is to be used (OD-S12-05 / 06, HAR-12) | keep holders empty; the Zone H gate stays unused | docs/30-release/release-approvals.md (AP-1); docs/30-release/environment-promotion-plan.md | OPEN

## Differences (11)
DV-01..DV-11: what changes between the legacy system and the hub (source: hub/coexistence/seed_s20.json). Your decisions are on 'Sign-offs (40)', rows AP-DV-*.
DV | Golden reference | Legacy value | Hub value | Justification in the register | Repo's recommended default
DV-01 | CT-12:batch.sql_report_1_total_gross | 742956.61 | 622826.44 | SQL report 1 total inflated by LEFT JOIN events fan-out (BB-08); new month_end_total sums cases once. F10-2 DV-01 (fix). | fix (adopt the hub figure) for CUT-4; keep legacy report running as comparator
DV-02 | CT-08:batch.partner_error_reasons[replayed source message] | 64 | {"NOOP_DUPLICATE":67,"REVISED_CONFLICT":0} | Legacy marks every REPLAY as DUPLICATE (BB-05); new distinguishes identical vs changed content. F10-2 DV-02 (fix). New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. Observed on the shipped feed: 67 REPLAY rows -> NOOP_DUPLICATE, 0 REVISED_CONFLICT (no changed-content replay exists in FX-BASE125; the changed-content path is covered by TST-INT-01..08). Legacy 64 vs 67: 3 REPLAY rows fail legacy key/schema checks first (BD-02). | fix
DV-03 | CT-08:batch.partner_error_reasons[quantity out of range] | 154 | {"NEGATIVE_VALUE_items":161,"flagged_value_queue":3} | Legacy rejects negative quantity; new keeps it flagged for review. F10-2 DV-03 (change of class). New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. 161 partner items carry NEGATIVE_VALUE and are kept (3 in queue flagged_value; the rest carry a higher-precedence reason), none rejected (BD-03). | change of class: adopt as built
DV-04 | CT-11:batch.java_tiny.stdout#count | "2390" | {"UNPARSABLE_AMOUNT":10,"kept_rows":2390} | Legacy Java silently skips blank amounts; new reports UNPARSABLE_AMOUNT (quarantine). F10-2 DV-04 (fix). New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. Vendor tiny CSV: 10 rows QUARANTINED UNPARSABLE_AMOUNT, 2,390 rows kept (BD-04). | fix
DV-05 | CT-13:batch.js_policy_table.allows[7:9] | [["abc","APAC",2026,false],[null,"APAC",2026,true]] | {"abc":"E-POL-INPUT-INVALID","null":"E-POL-INPUT-INVALID"} | Legacy JS tolerance with 'abc'/null is undefined behaviour; new rejects invalid input. F10-2 DV-05 (fix). | fix
DV-06 | CT-13:batch.js_policy_table.table[0] | ["APAC",2019,999999] | {"defaulted":true,"region":"APAC","threshold":999999,"year":2019} | Unknown region/year default 999999 kept but marked defaulted. F10-2 DV-06 (additive). | accept the additive marker
DV-07 | CT-08:batch.partner_status_after_all | [["ACCEPTED",7917],["DUPLICATE",64],["REJECTED",586]] | {"legacy_table":"untouched","outcome_store":"append-only","outcomes":{"EXCEPTION":8109,"NOOP_DUPLICATE":67,"QUARANTINED":223,"VALIDATED":165,"VALIDATED_WITH_FLAGS":3}} | Legacy reconcile overwrites processing_status in place; new appends outcomes and leaves the legacy table untouched. F10-2 DV-07 (fix). New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. DV-07a (Stage 17 PCH-35 text extension): the new value also includes the outcome classification: EXCEPTION 8,109 (UNMATCHED_REF 7,903, NO_BUSINESS_KEY 206 - see DV-10), QUARANTINED 223, VALIDATED 165, VALIDATED_WITH_FLAGS 3, NOOP_DUPLICATE 67 (BD-07). | fix, after Dinesh has seen the 7,903 UNMATCHED_REF volume
DV-08 | CT-10:batch.shift_distinct_objects_in_first_500_joined_rows | 118 | 500 | Night-shift join multiplies rows (118 distinct objects in first 500); new evaluates per entity (500 distinct in first 500). F10-2 DV-08 (fix). | do not cut over this figure; keep legacy authoritative until a hub job exists
DV-09 | CT-07:lib.missing_field | {"accepted":0,"duplicates":0,"invalid":1,"received":1} | {"quarantined":1,"reason":"MISSING_ENVELOPE_FIELD","received":1} | Legacy counts invalid gateway events but does not store them; new stores them in quarantine. F10-2 DV-09 (fix). Stage 20 label correction (Stage 17 PCH-35, OD-24): the built intake uses the Stage 12 code MISSING_ENVELOPE_FIELD, not 'envelope_invalid' (BD-09). New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. | fix, with the corrected label
DV-10 | CT-08:batch.partner_status_after_all[ref_id match] | [["ACCEPTED",7917],["DUPLICATE",64],["REJECTED",586]] | {"linked":168,"no_business_key":206,"unmatched_ref":7903} | Legacy reconcile never checks ref_id, so most partner rows end ACCEPTED; the hub links ref_id to the 125 baseline cases by exact key (BEH-INT-08, AC-INT-18): 168 linked, 7,903 EXCEPTION/UNMATCHED_REF, 206 EXCEPTION/NO_BUSINESS_KEY. Specified behaviour (PRD baseline OD-22) registered by Stage 17 PCH-35 / OD-24 as proposed DV-10 (BD-07). Registration only, not approval. New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. | fix (exact match, BEH-INT-08)
DV-11 | DEV-29:js.threshold(APAC, partial year) | {"":15000,"2":15000,"202":15000} | {"":{"defaulted":true,"threshold":999999},"2":{"defaulted":true,"threshold":999999},"202":{"defaulted":true,"threshold":999999}} | Legacy JS threshold lookup matches partial years by startsWith (threshold('APAC', 202 / 2 / '') -> 15000, the 2022 row); the rule service requires the 4-digit year and returns 999999 with defaulted = true (DEV-29, RTD-41). No Stage 7 golden captures it: the legacy value is the documented INC-04 S05 live node run (docs/15-modernization/transformation-log.md DEV-29). Registered by Stage 17 PCH-35 / OD-24 as proposed DV-11 (BD-10). Registration only, not approval. New value restated in Stage 20 as the OBSERVED output of the built module on FX-BASE125 (DW-04, golden-compare provider 'observed'); the behaviour described is unchanged. | fix (4-digit year required)
Note for DV-08 | The repo's recommended default for AP-DV-08 is 'do not cut over this figure; keep legacy authoritative'. The golden comparison still reports the difference as UNAPPROVED until the DV-08 row is approved, so G1 cannot pass while it is OPEN. Approving it for G1 acknowledges a known difference in SHADOW mode only; the cutover decision stays with AP-CUT-4. Please decide which you want.

## Security (T-10)
T-10: every High vulnerability and every open High finding needs a decision recorded by the Engagement lead (go-no-go-criteria.md).
Item | What it is | State today | Option 1 | Option 2 | Claude's suggestion (not a decision) | YOUR CHOICE (1 / 2 / OTHER) | Reason / OTHER text
VR-02 | Python 3.10 is end of life (floor shipped at 3.10) | MITIGATED + ESCALATED (D-27-02). 3.12 floor is selectable; CI file for 3.12/3.13 written but not installed. | Accept: stay on the 3.10 floor for shadow on this laptop; no exposure, no real data. | Adopt a 3.12 floor before release. Evidence from this session: the full regression passes on 3.14 (see Technical sheet) but 3.12 itself was not run. | Option 1 for a shadow release on synthetic data, with 'before any exposure or real data: move to 3.12+' written into the decision.
VR-03 | No TLS (hub binds loopback only) | MITIGATED by avoidance: non-loopback bind refused by two independent checks. | Accept: loopback-only; any exposure is a new decision. | Require TLS before release. | Option 1. The risk exists only if the hub is exposed, which the release scope excludes.
VR-04 | Legacy Dockerfile / compose run as root and bind all interfaces if started as shipped | DEFERRED to Stage 30 (D-27-06). Frozen legacy path. | Accept: leave the legacy files unchanged; hardened recipe stays a proposal (deployment-strategy DS-5); do not start the legacy containers. | Harden the legacy files now (changes a frozen legacy path). | Option 1.
F-11 | Red-team finding S26-F-11: group wall times 145-174 s against the 180 s per-call cap | Open; listed as LOW in red-team-findings.md although the criterion text mentions it. Please confirm it belongs in T-10. | Accept / backlog: the cloud regression has no cap (this session ran every group without it). | Split the two slow groups (E26, S26). | Option 1; note it is Low severity in the findings table.

## Monitoring (T-09)
T-09: monitoring coverage for the release window (persisted metrics, alert delivery, an owner)
Option | What it means | What changes in the repo | Effort | Claude's suggestion (not a decision) | YOUR CHOICE (A / B) | Reason
A | Accept manual monitoring for the release window: you run RB-00 at the start and end of each working session; no alert delivery; you are the owner (AP-OPS-05, D-31-08). | Nothing in code. A dated acceptance is recorded (draft supplied). The criterion text allows this: 'or by Dinesh explicitly accepting manual monitoring'. | ~10 min of your time | A for a single-person shadow release.
B | Wire periodic persistence of HTTP metrics (D-31-01) and the six gap metrics (D-31-06) so alerts can be evaluated from stored data. | Edit hub/web/app.py and hub/obs wiring; new tests; AP-OPS-10 becomes 'wire before release'. Alert delivery and on-call would still not exist. | ~1 h Claude + review | Not needed for shadow; consider before any real use.
Note | If you choose A, also set AP-OPS-05 and AP-OPS-10 on the Sign-offs sheet consistently (AP-OPS-05 = manual evaluation; AP-OPS-10 = release without wiring).

## Path to GO
Three levels of GO
Level | Meaning | Technical criteria | Approvals needed | Your time | Status
GO (shadow) — 'Partial Go' | Hub runs beside legacy on synthetic data. No production cutover. | G1, T-05, T-09, T-10 must flip to pass (16 already pass) | 22 REL approvals (AP-REL-01, AP-GATE-G1..G10, AP-OPS-01..11) + 11 deviation decisions for G1 | ~60-75 min | see Start here counts
Limited GO — rule evaluation only (CUT-2) | Hub rule evaluation becomes authoritative for the three policy differences. | As above | GO (shadow) set + AP-CUT-2, AP-DV-05, AP-DV-06, AP-DV-11, AP-OPS-12 (named consumers) | + 30 min plus a named consumer | not started
Full GO | All five capabilities authoritative. | As above | All 40 approvals + open decisions OD-S12-xx, definitions OPD-01/02/08, Zone H holders | days; needs real org inputs | out of scope today